# MINUTES - the 1st meeting of partners

Venue: Slovak University of Technology, Mechanical Engineering Faculty, Dept. of Maths

Nám. Slobody 17, 812 31 Bratislava, Slovakia

Date: November 3 - 4, 2006

### Present:

Velichová Daniela, Slovak University of Technology in Bratislava, SK

Snezhana Georgieva Gocheva-Ilieva, Plovdivski University of Plovdiv, BG

Pavel Martínek, West Bohemian University, Plzeň, CZ

Gerardo Rodriguez, University of Salamanca, ES

Päivi Siltanen, Tilossilos Ltd., Tampere, FI

Péter Körtesi, University of Miskolc, HU

Olivia Gill, University of Limerick, IE

Daniela Richtáriková, Slovak Society for Geometry and Graphics, Bratislava, SK

Duncan Lawson, Coventry University, UK

Peter Kostka, Slovak University of Technology in Bratislava – vice dean, SK

Pavol Krempaský, Slovak National Agency of LvD, Bratislava, SK

Friday, November 3, 2006

## Agenda

10.00 Opening – presentation of partners

10.30 Presentation of P. Krempaský, representative of the Slovak National Agency of Leonardo da Vinci programme

11.20 Contractualisation and management details

13.30 Lunch

15.00 EVLM workplan - improvements and enhancements, distribution of work, deliverables, interim evaluation and reporting

17.00 Information about architecture of the main EVLM framework and database solution,

security system and communication priorities – drafts

17.30 Administrative and financial handbook

19.00 Dinner for all partners

Each project partner was provided by the Handbook which contained:

- Programme of the Kick-off Meeting

- List of Partners with contact details

- Contracts

- Financial Information Form (Bank Details)

- Management details

- Reporting Procedures - calendar

- Reporting Forms, Time Sheet

- List of Deliverables

- Financial agreements

- Work plan

- Presentation of the Slovak National Agency of LvD representative

Partners briefly presented themselves and their institution, and outlined their main expectations, foreseen achievements and results of the cooperation in the partnership.

## Discussion, decisions, assignments:

### 1. Contractualisation and management details

### CONTRACTS

The contractor will send to partners:

- Last page of the contract with NA – signed, November 7, 2006

- Contracts with partners - doc files + annexes (Bank form word file, Workplan)

- Contracts with partners - printed originals in 2 copies + annexes

- Signed contract – 1 copy

The partners will send to the contractor:

- Names of official representatives,

- VAT, REG numbers, ASAP

- Comments to annexes (Workplan) –

- available free-ware products, links

- corrections of English – partner P9

- Signed contracts (2 copies) + Bank form

Suggestions:

- to specify deliverables in the tasks of chapters creation and translation

### INTERIM REPORTING

Contractor will provide partners with:

- Interim report form – word file,

- Timesheet – word file,

- Financial tables – excel files,\

- Deliverable FrontPage – word file,

- Minutes 1 – Kick-off meeting -Word file

- PowerPoint presentations

- Reminder: 2 weeks prior to deadline for sending report – email message

Partners will send to contractor:

- Interim report 1, 2, 3, 4, 5 printed and signed + word files,\

- Financial report 1, 2, 3 - printed and signed + excel file + all relevant documents

- Deliverable FrontPage – printed and signed + sample copies of the deliverable

- Copies of travel documents – tickets, signed translation

### WORK on the PROJECT

Main deadlines for the first year

| Project webpages | January 15, 2006 (month 3) |
| --- | --- |
| EVLM portals | March 15, 2007 (month 6) |
| Database operational manual | July 15, 2007 (month 10) |
| Information leaflets | August 15, 2007 (month 11) |
| Collection of consultancy topics (in the database) | September 15,2007 (month 12) |
| National Centres of Mathematics | 15, October 2007 |
| Interim reports | March 15, 2007 June 15, 2007 September 15, 2007 |
| Financial reports | September 15, 2007 |
| Evaluation report | October 15 2007 |
| Interim overall report | October/November 2007 |

Filled in reporting forms should be sent to the Co-ordinator within 15 calendar days after the end of the reporting period

### ACTIVITIES in the 1st year - Suggestions

Conferences to be attended:

- SEFI and IGIP Joint Annual Conference July 2007, Hungary (Peter Körtesi)

Other dissemination ideas:

Materials:

- creation of leaflets available in English and national languages 5000 pcs

Each partner will be responsible for national mutations and also for creation of some issues in English.

- dissemination booklet cca 6 pages for Sefi seminar (April 2008)

### 2. EVLM workplan - improvements and enhancements, distribution of work, deliverables, interim evaluation and reporting

### Deliverables Suggestions:

- to produce DVD or memory sticks instead of CD (Päivi Siltanen)

- to split item of chapters number in deliverables into  2 items: chapters to be created and chapters to be translated (Peter Körtesi, Duncan Lawson)

Discussion:

Will created portals be free or paid?

- they should produce money for maintaining (Peter Körtesi)

- experiences

  - portal is paid by university (as a kind of promotion) (Snezhana Gosheva, Gerardo Rodrigues)

  - portal is paid from other projects (Duncan Lawson)

### Interim evaluation and reporting

Reporting forms:

- Interim report form + Time sheets

- Financial report form

- Front page for deliverables

Decisions:

- Interim report form will include a timesheet for every person employed in the project. It should correspond to plan of activities and budget

- financial report will include official version of xls tables

Interim report form:

- Project name and number

- Project start and duration

- Active period of the reporting

- Description of the work and activities

- Description of products

- Partner

- Signature of the responsible partner

- Time sheet – number of hours on project per days (month) according to the planned distribution of staff days to work packages

Financial report form:

Active period of reporting + Partner Description of all expenditures

1. Staff costs

2. Travel costs – originals of tickets must be provided

3. Production costs

4. ICT costs

5. Other costs

Copies of all relevant expenditures must be provided

6. Overheads - since covered by an agreed maximum of 7% of the total contractually agreed budget (which is fixed at the time of contracting and which cannot change in the course of the project) no supporting documents need be produced.

Signature of the responsible partner

### Reporting on deliverables

- List of deliverables + deadlines

- Front page for deliverable

- Project name and number

- Project start and duration

- Deliverable type, name description

- Signature of the responsible partner

- Dissemination level

### Financial issues:

Consolidates budget of the project:	379 621,00

Community financial contribution:	284 716,00  (75%)

Partners own funds:		 	  94 905,00  (25%)

Budget distribution:

Staff costs:				231 418,00

Community staff contribution:	162 616,00

Partners own funds:			  68 802,00

Travel costs:			  	  40 000,00 (100%)

ICT costs:			  	  40 100,00 (100%)

Production costs:			  30 000,00 (100%)

Other costs:			  	  12 000,00 (100%)

Overheads:			  	  26 103,00 (partners own funds)

Pre-financing 40% of the budget

-within 45 days following the signature of the contract

- distributed among the partners based on their share in the whole budget

Next payment

30% of the Community grant on request

- only if we have used more than 70% of the pre-financing in the first year and the reports are OK

Final payment

- after the project evaluation, if the score is within 5 - 10 points

### Work plan

Next meetings:

January 25-28, 2007	- Coventry

June 7-9, 2007 	- Salamanca

Websites: major platform for dissemination

Project Main Portal: partnership virtual workplace and communication environment

National Centres of Mathematics: local workplace for partners

List of Workpackages

| Work-package | Timetable | Months | Responsible Partners | Results, Outcomes |
| --- | --- | --- | --- | --- |
| WP1 Organisation and management planning Competence enhancement | X – XI 2006 | 2 | P1, P9 - English websites, P2 - P8 - national versions | Project website design 1M. Kick-off meeting – P1 |
| WP2 | X – XII 2006 | 3 | all | EVLM portal design |
| WP3 | I – III 2007 | 3 | P1, P3, P8, P9 | Database system development 2M. Database meeting – P9 |
| WP4 | IV – VI 2007 | 3 | P1, P3, P8 | Installation of servers |
| WP5 | VI – VII 2007 | 2 | P1, P3, P8, P9 | Testing the functionality Database Operational manual |
| WP6 | VII – IX 2007 | 3 | all | Populating the Central / National Databases and their updates |
| WP7 | X 2007 | 1 | P1 - P7 all | Launching the National centres of Mathematics Dissemination booklets and information leaflets production |
| WP8 | I – IX 2007 | 9 | P1, P4, P9 | Translations Interim evaluation 3M. Dissemination meeting – P4 |
| WP9 | X – XII 2007 | 3 | P1 - P7 | Training tutorials for teachers |
| WP10 | X– XII 2007 | 3 | all | Teacher’s guide – CD 4M. Workshop I – P2 |
| WP11 | X 2007 – IX 2008 | 12 | P1 - P8 | Assistance to students, expert consultancy |
| WP12 | I – III 2008 | 3 | all | Student‘s book – CD 5M. Workshop II – P7 |
| WP13 | VII 2007 - IX 2008 | 12 | all | Database updates 6M. Valorisation meeting – P6 |
| WP14 | VI– IX 2008 | 6 | all | Valorisation results , feedback analysis |
| WP15 | IX 2008 | 1 | P1, P6, P9 | Overall evaluation 6M. Valorisation meeting – P6 |

List of activities and responsible partners

- Project website design (national versions)				P1, P9 (P2 – P8)

- EVLM portal design (national portals)					all

- Development of the central database system 				P1, P3, P8

- Installations of Servers – central, webMathematica 			P1, P3

        - – national 					P2 – P8

- To populate databases							all

- Database Operational manual production				P1, P3, P8, P9

- To test functionality of the EVLM network				all

- Launching of the National Centres of Mathematics			P1 – P7

- Creating mathematical resources for the Databases			P1 – P7

- Continuous update and maintenance of the Databases			all

- Providing expert consultancy for target groups or individuals		P1 –  P7, P9

- Teacher’s guide book CD production					all

- Student’s work book CD production					all

- Feedback analysis and valorisation plan					P9

- Evaluation of the project results						P1, P9

- Production and dissemination of the leaflets, booklets			all

Plan of meetings

- Kick-off meeting 				coordinator P1, Work-package 1

SK (Bratislava), November 3 - 4, 2006

PROGRAMME: Organisation and management planning

Competence enhancement

Project website design

- Database meeting – brainstorming         	 partner P9, Work-package 3

UK (Coventry), January 25 – 27, 2007

PROGRAMME: Discussion about the database contents

Visit to the working Math centre at Coventry University

Brainstorming and EVLM functionality planning

- Dissemination meeting			partner P4, Work-package 8

ES (Salamanca), June 2007

PROGRAMME: Discussion about the available e-learning materials

Dissemination strategies – national translations, reports on conferences, leaflets and booklets, posters, web forum

Valorisation keynotes and valorisation strategic plan, Interim reports

- Workshop I        				partner P2, Work-package 10

BG (Plovdiv), October 2007

PROGRAMME: Preparation of teacher‘s guide book

- Workshop II					partner P7, Work-package 12

ER (Limerick), March 2008

PROGRAMME: Preparation of student‘s work book

- Valorisation-Evaluation meeting 		partner P6, Work-package 13

HU (Miskolc), June 2008

PROGRAMME: Project Dissemination, Promotion and Valorisation Plan results

Interim partner’s reports, interim evaluation reports

7.	  Last meeting 				partner P5, Work-package 14

FI (Tampere), September 2008

PROGRAMME: Overall evaluation of the project work and results

Planning of the further activities

EVLM functionality and extension

Calendar of deliverables

| MONTH | DATE | TYPE | PARTNERS |
| --- | --- | --- | --- |
| 3rd | January 15, 2006 | Project webpages | all |
| 6th | March 15, 2007 | EVLM Portals | all |
| 10th | July 15, 2007 | Database Operational Manual | P1, P3, P8, P9 |
| 11th | August 15, 2007 | Dissemination leaflets production | all |
| 12th | September 15, 2007 | Collection of consultancy topics | P1 – P8 |
| 13th | October 15, 2007 | Launching National Centres of Mathematics | P1 - P7 |
| 14th | November, 2007 | Overall report 1 | P1, P9 |
| 15th | December 15, 2007 | Teacher’s guide book CD | all |
| 16th | January 15, 2008 | Electronic questionnaire forms for feedback | P9 |
|  |  | Information booklets production | all |
| 17th | February 15, 2008 | Feedback collection from trained teachers | P1 – P7 |
| 18th | March 15, 2008 | Student’s workbook CD | all |
| 20th | May 15, 2008 | Feedback analysis 1 | P9 |
| 21st | June 15, 2008 | Feedback collection from students | P1 – P7, P9 |
| 23rd | August 15, 2008 | Feedback analysis 2 | P9 |
| 24th | September 15, 2008 | Updated list of consultancy topics in the databases | P1 – P8 |
| 25th | October 2008 | Final report | P1, P9 |

### 3. main EVLM framework and database solution

Partners will study materials included in the Handbook and prepare their suggestions to final discussion for the second meeting – Database meeting – brainstorming held on January 25-28, 2007 – Coventry, UK

### 4. Administrative and financial handbook

is available on http://ec.europa.eu/education/programmes/leonardo/handbook_en.html

Questions:

- How can be usage of existing equipment for purposes of the project calculated?

(Mr. Krempaský promised to find out)

- Is it possible to rearrange personal costs within the type (manager, teacher, admin., ..) and number of days of work? (yes)

- Are Subsistence Costs for days waiting for the nearest return flight eligible? (yes)

- Can be maximum daily Subsistence Costs modified according to the real demands? (No)

Saturday, November 4, 2006

## Agenda

10.00 EVLM websites and main portal design – suggestions

10.30 Software support – including xml / MathML editors, webMathematica and other CAS,

open source software solutions, search for existing and new ICT usage, presentation of SciWriter, Publicon

11.00 webMathematica servers and their usage

12.00 End of the meeting

## Discussion, decisions, assignments:

### EVLM WEBSITES AND MAIN PORTAL DESIGN

First version of the project Webpage in English is available on the address

http://www.matematika.sjf.stuba.sk/EVLM/index.htm

with the following structure

Main page

Description of the project – logo + Leonardo da Vinci logo

Aims

Objectives

Impact

Results

Outputs

Target groups

Partners

Links

Central portal will be developed under the responsibility of coordinator P1 and partners P3, P9. National portals (mirrors of central portal in national languages) are completely under the responsibility of partners P2, P3, P4, P5, P6, P7, P8.

| Contractor to partners | Partners to contractor |
| --- | --- |
| Webpage in English First version available | Improvements November 30,2006 |
|  | Text of one item in the main menu / partner, December 15, 2006 |
| Final Webpage in English December 31, 2006 | Webpages in National languages January 15, 2006 |
| Central EVLM portal in English Draft - delivered | New ideas – Meeting 2 (database contents), January 2006 |
| Central EVLM portal in English February 28, 2006 | National portals March 31, 2006 |

The partners will send to the contractor and Partner 9:

- Webpage improvements and comments, communicated by e-mails

Deadline: November 30, 2006

Contractor and Partner 9 will compile suggestions and create a possible new structure.

They will distribute separate items to partners to develop relevant text.

Each partner will write text of one item

Deadline: December 15, 2006

Partners P1, P3, P9 will develop the Main project webpage in English.

Deadline: December 31, 2006

Partners P2, P3, P4, P5, P6, P7, P8 will develop national mirrors – national versions of the project webpage, which must include translation of the source text into national language and some additional pieces of information relevant in the national context.

Deadline: January 15, 2006

Structure of the EVLM portals will be discussed during meeting 2.

### Software support

Presentations of software solution for production of xml files with embedded MATHML coding of mathematical formulas:

a) Presentation of SciWriter editor – D. Velichová

b) Presentation of Publicon - M. Kováčová

### webmathematica server and its usage

Presentation of webMathematica with technical details and examples - P. Martínek

done in Bratislava, November 10, 2006

Drafted by: Daniela Richtáriková, Partner 8, team leader

Confirmed by: Daniela Velichová, Project coordinator