# MINUTES from the 4th meeting of partners

Venue: Plovdiv University of Paisii Hilendarski, Faculty of Mathematics and Informatics Tzar Assen street 24, Plovdiv, Bulgaria

Date:   October 11 - 12, 2007

### Present:

Velichová Daniela, Slovak University of Technology in Bratislava, SK

Snezhana Georgieva Gocheva-Ilieva, Plovdivski University of Plovdiv, BG

Gerardo Rodriguez, University of Salamanca, ES

Péter Körtesi, University of Miskolc, HU

Olivia Gill, University of Limerick, IE

Patrick Johnson, University of Limerick, IE

Daniela Richtáriková, Slovak Society for Geometry and Graphics, Bratislava, SK

John Goodband, Coventry University, UK

Absent with excuse:

Jiří Benedikt, West Bohemian University, Plzeň, CZ

Absent without excuse:

Päivi Siltanen, Tilossilos Ltd., Tampere, FI

Thursday, October 11, 2007

## Agenda

10.00  Opening - presentation of the coordinator – information on work progress

Management - financial and other organisational issues

Collecting Timesheets, Interim reports, Delfrontpages, other supportive materials

14.00  Lunch

16.00  Presentations of EVLM National portals, partners P2 – P8:

Partner 2 – Bulgaria

Partner 4 – Spain

Partner 6 – Hungary

Partner 7 – Ireland

Partner 8 –Slovakia

17.30 Coffee break

17.45 Presentations of Central portal updates, Project office on-line – Partner 1

19.00 Dinner

## Discussion, decisions, assignments:

### 1. Presentation of the coordinator – information on work progress

Coordinator Mrs. Daniela Velichova opened the meeting, she explained absence of the partner 2 contact person Mr. Jiří Benedikt and informed about having no information from the partner 5 representative, Mrs. Päivi Siltanen. Then she outlined the work done so far.

### Management - financial and other organisational issues

Mrs Velichova recapitulated the complete information about all materials required from partners for the 1st evaluation report:

- 3 interim reports

- financial tables

- deliverables on:	- project national webpage

- leaflet

- national portal, accompanied with www address

- list of topics in central database (according to the agreement in Salamanca)

- list of topics and educational materials in national database

- list of dissemination activities during the 1st year – each activity has to be supported by some kind of evidence

- materials for EVLM database structure CD: - folder of  National Project webpages

- folder of National Portal webpages

- timesheets - signed

All partners were asked to upload their materials in e-form on the EVLM server, brought materials were collected and missing materials are to be posted in paper form to coordinator till the end of October.

Next meeting:

The next meeting was shifted to

February 14-15, 2008 - Limerick (presentation of Teacher’s guide book & Workshop II – Student’s guide book)

### 2. Presentations of EVLM National portals

The partners P2, P4, P6, P7, and P8 presented their EVLM National Portals.

Each portal has to display LdV non-responsibility logo and contain the link to the Central portal.

### 3. Presentations of Central portal updates, Project office on-line

The coordinator presented the updates of the central portal and instructed all partners how to add a file into the central database. Each database input is accompanied by information questionnaire.

The following items were discussed in connection to the central database structure:

- subjects and topics updates

- layout of titles in hyperlink menues: right – left alignment

- suggestion to use “Contact us” button instead of the direct e-mail address

Friday, October 12, 2007

## Agenda

9.00 Overall discussion and final agreements on deadlines

10.30 – 12.00 Presentations of partner’s contributions to the Teacher’s guide book

Partner 1 – 2 chapters

Partner 2 – 2 chapters

Partner 4 – 2 chapters

Partner 6 – 2 chapters

Partner 7 – 2 chapters

13.00 Closing, Lunch

## Discussion, decisions, assignments:

### 1. Overall DISCUSSION AND final agreements on deadlines

Summary:

- 15th October 2007 is the first day of the project second year

The coordinator will be supplied with:

- 3 reports and 3 deliverable frontpages (project, leaflet, portal) in 1 original and 3 copies + the leaflet sample

- financial table –filled in coordinance to the Administrative and Financial Handbook (all expenses including) – uploaded on the server

- timesheets – 2 originals

- travel documents – 1 copy

- invoices – 1 copy

- translations of invoices – signed

and with:

- changes in database topics according to the available materials

- list of dissemination activities (attended conferences - supported by the paper or ppt - presentation)

- workplan for the project 2nd year

- list of educational materials in English uploaded to the EVLM Central database

Deadline: 31st October

Next:

- With respect to the deadline of Teacher’s Guide Book and Student’s Guide book the date of Limerick meeting was proposed to be shifted sooner.

- Mr. Goodband will create the EVLM group within the Facebook. The 1st week in the month was proposed to be the time for the project partnership chat communication.

Information booklet

- Information booklet (format A5) is aimed to be presented at the Loughborough SEFI Conference. It would provide more information for teachers and would be more about contents. The proposal will be prepared by the Partner 9 and it will be discussed during the Limerick meeting.

Teacher’s Guide book

- The deadline for the first chapters of Teacher’s Guide book is November 10.

- The deadline for the second chapters of Teacher’s Guide book is December 10.

- The deadline for completion and the introduction chapter is January 30.

- The guide book is designated  to be published on web. The web formats (xml, html, xhtml and MathML coding, etc) are preferred. For CD or DVD publishing the files will be converted into text or printscreen output. The language correction will be done in text format (pdf, doc, tex).

- The chapters will be sent to the partner 9 (Mr. Duncan Lawson) in pdf or other text format and at the same time also in origin format to all other partners (P1-P8) in order to allow them to start the translation work.

Database search

- Authors of the database document input will be asked to create an XML meta-data file (txt) and send it to Mr. Benedikt. The sample is as follows:

<?xml version="1.0" encoding="windows-1250"?>
<record xmlns:xs="http://www.w3.org/2001/XMLSchema-instance" xs:noNamespaceSchemaLocation="record.xsd">
<targetGroup>students</targetGroup>
<subject>Calculus\Integration</subject>
<documentType>PDF</documentType>
<author>Benedikt Jiri</author>
<description>integration in R</description>
<file>integraly.pdf</file>
</record>

Further information can be found on: http://home.zcu.cz/~benedikt/EVLM/comments.html

### 2. Presentations of partner’s contributions to the Teacher’s guide book

The partners (P1, P2, P4, P6, and P7) presented their proposals of two chapters included in the Teacher’s Guide Book.

Themes:

P1 - Slovakia:

Ch1: What one can expect from webMathematica (Examples)

Ch2: Step by step guide on how to create jsp documents

P2 -Bulgaria:

Ch1- Introduction to Mathematica

Ch2 – Mathematica in Examples

P4 - Spain:

Ch1- Advanced usage of Mathematica

Ch2- Examples

P6 - Hungary:

Ch1: Why to use computer algebra systems

Ch2: How to use history of mathematics to enhance student interest in mathematics, or

Introduction to Maple

P7 - Ireland:

Ch1: How to use GeoGebra

Ch1: Examples

In Bratislava, October 30, 2007

Daniela Richtáriková						Daniela Velichová

partner 8						project coordinator